## Slide 1: APARTTMENT FINDING SYSTEM
SOFTWARE PROJECT 1

## Slide 2: Group information
Name | ID
Jahan, Effat | 18-38718-3
Tanjin, Merina | 18-37783-2
Saha, Manik | 18-38965-3
Mim, Fyzun Naher | 18-36446-1

## Slide 3: motivation
Making a system where users don’t have to rely on other people to contact about a certain property
Making a system with multiple features so customer will find everything in one place
As a pandemic devastated the entire world. There are people who lost their job or cannot afford the current place or on a position where they need to shift the current home. In this scenario looking for apartments manually by going to certain areas where there is lockdown is not an option. So, we took the whole process in online and digitalized it.
In case of emergency apartment hunting relying on a third party can be frustrating.
Looking for apartments within budget in 5/6 areas is absolutely tiring. Where in online it’s just one click away

## Slide 4: Introductions
In this technology based society everything is being digitalized. Changing home is particularly very tiresome. From looking for a suitable home manually and confirming to the final moving day everything is a huge hassle. The goal of our study is to develop a system to solve this issue.
This is a smart apartment finding system where customer can acquire our service from anywhere with a click of a button. This will make house shifting much easier.

## Slide 5: System Features
View apartment listing for free
Choosing and booking apartment is just one click away
Making the system more user friendly where user can directly contact home owner and choose their home
Instant and online transactions
Recommendation for suitable apartment based on requirements
Updating and editing user profile
Other service will be available for the customers
Checking monthly revenue for admin
Add new user
Review services

## Slide 6: Resource:
There are two kinds of resources. One is hardware and the other one is software. All resources needed is provided below.
    Hardware
    Software

## Slide 7: Hardware
Minimum requirements for server:
Processor: Xeon based microprocessor (2.0 GHz or faster recommended)
Ram: minimum 16 GB
System type: Linux (64 bits)
Storage: minimum 1TB SSD or higher.
For Storage Service: Network File System (NFS)
Minimum requirements for client:
Processor: Dual-core.
RAM: 2 GB.
System: Windows, MAC OS X, Linux.
Web Browser: Firefox, Google Chrome, Opera

## Slide 8: Software
Text editor like Notepad++, Sublime Text, VS code.
C#, Microsoft SQL server.
Web Browser: Firefox, Google Chrome, Opera.

## Slide 9: Operating Environment
The whole system will be operated from the external Linux Server.
This website is platform independent user can use it from any kind of internet operate devices.
User application is accessible through various kinds of browsers (Opera, Mozilla Firefox, and Google Chrome etc ).
IBM or MAC or Windows any user from any platform can use.
Operating System can be used Windows of any version from Windows 98, Windows XP/Vista to Windows 10, MAC OS X 10.5 or above.

## Slide 10
House cleaning options
Easy Of changing home
Fast & safe booking
Save time
Online payment
Can buy apartment
Find apartment from home
Fully online
No physical activities
Easy house shifting
Less expensive
Easy contact with apartment owner
Can advertise for apartment
Chatting
Apartment review
Easy access from anywhere & any device
Benefits of the system

## Slide 11
Diagram

## Slide 12
Use case diagram

## Slide 13
Activity Diagram
Login Activity
Diagram
Admin Activity
Diagram

## Slide 14
Activity Diagram
Manager Activity
Diagram
User Activity
Diagram

## Slide 15
Login UI
Homepage
Prototype

## Slide 16
Search Apartments
Apartments Details
Prototype

## Slide 17
Prototype
Apartment Owner Dashboard
Post New Apartments

## Slide 18: Project Planning
Collect all the requirements
Think of our plan as a roadmap for stakeholders
These stakeholders might include:
The project manager, The customer, The team
Break the project into a list of deliverables
Talk to our team
Identify risks
Create a budget
Set progress reporting guidelines

## Slide 19: Schedule and budget
Front-end activities (40-50%)
Construction activities (15-20%)
Testing and installation (30-40%)
Total days for development: 138 working days
Total time for development: 8 months

## Slide 20: Budget
Items | Daily Cost (BDT) | No. of Days | Total Cost (BDT)
Front-end developer | 650 | 96 | 62,400
Back-end developer | 750 | 88 | 66,000
Business engineering | 400 | 25 | 10,000
Total development cost |  |  | BDT 138,400
Overhead Cost (20%) |  |  | 27,680
Safety net for spillover (8%) |  |  | 11,072
Cloud Server |  |  | 260,000
Net cost |  |  | BDT 437,152

## Slide 21: Schedule
Tasks | MONTH 1 | MONTH 2 | MONTH 3 | MONTH 4
Collecting Requirements | 1/8/2021 to 15/8/2021 |  |  | 
Team Preparation | 8/8/2021 to | 12/9/2021 |  | 
Analyzing project |  | 12/9/2021 to 30/9/2021 |  | 
Overall Process Design |  | 12/9/2021 to 30/9/2021 |  | 
Technology Choosing |  | 25/9/2021 to | 10/10/2021 | 
Analyzing Scenarios |  | 25/9/2021 to | 25/10/2021 | 
UML Designs |  | 25/9/2021 to |  | 28/11/2021
Database Design |  | 25/9/2021 to |  | 15/11/2021

## Slide 22: Schedule
Tasks | MONTH 5 | MONTH 6 | MONTH 7 | MONTH 8
Front-end design | 1/12/2021 to 20/12/2021 |  |  | 
Back-end and API design | 15/12/2021 to | 15/1/2022 |  | 
Connecting front and back |  | 10/1/2022 to 30/1/2022 |  | 
Testing |  | 10/1/2022 to 30/1/2022 |  | 
Error solving |  | 15/1/2022 to | 10/2/2022 | 
Testing |  | 15/1/2022 to | 20/2/2022 | 
Upgrading |  | 15/1/2022 to |  | 30/3/2022
Integrating |  | 15/1/2022 to |  | 22/3/2022

## Slide 23: Risk Management
Some common risks are:
• Inaccuracies in the time and resource estimations.
• Scalability of the core framework architecture.
• Sudden change of requirements.
• Government rule changes.
• More focus on technical complexity, rather than user experience.

## Slide 24: Risk management plan
Risks | Probability | Rating
Project Manager Availability | 50% | Medium
Schedule slips | 70% | High
System goes hour | 60% | Medium
Project canceled | 30% | Low
False feature rich | 40% | Low
Programmers doesn’t have good experience | 50% | Medium
Late delivery | 50% | Medium
Customer Participation in Beta Testing | 30% | Low

## Slide 25: Conclusion
This apartment management system has been developed based upon the studying common scenario and web applications of similar kind. In this document we tried to provide solutions for the problems we came across in similar existing websites. If the budget and timeframe can accommodate more features then there will be changes in this document and development process.

## Slide 26: references
M. Nosworthy, G. Blanchard, R. Tripad, “bproperty,” 2015, https://www.bproperty.com/
C. Capital, F. Partners, “perforce.com”, 2014, https://www.perforce.com/blog/alm/how-write-software-requirements-specification-srs-document
J. graph, “appdiagram.com”, 2005, https://app.diagrams.net/
D. Field, “UI design”, 2016, https://www.figma.com/files/recent?fuid=1001531349736242039
Wikipedia, “software development", last edited 30 July, 2021, https://en.wikipedia.org/wiki/Software_development
M. Mohtashim, “tutorialspoint”, 2006, https://www.tutorialspoint.com/software_engineering/software_project_management.htm
M. Mohtashim, “tutorialspoint”, 2006, https://www.tutorialspoint.com/software_engineering/software_requirements.htm
B. Smith, “landing,” 2019, https://www.hellolanding.com/blog/apartment-hunting-tips/
A. Stringer, C. Stringer, “Molly maid”, 1979, https://www.mollymaid.com/our-services/apartment-cleaning/
A. I. Halim, “sheba.xyz”, 2015, https://www.sheba.xyz/house-shifting-service
S. Jain, “geeksforgeeks”, 2008, https://www.geeksforgeeks.org/software-engineering-software-quality-assurance/
Wrangler Topco. LLC, “time management”, 2006, https://www.wrike.com/project-management-guide/faq/what-is-time-management-in-project-management/

## Slide 27
THANK YOU